## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
MILESTONE | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
|  | 1 | 2 | 1 | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Requirement Analysis & Planning | Define project objectives & scope | 1 | 3 | 1 | 3 | 100 | bar: PERIODS 1 to PERIODS 5
| Identify AWS security services & integrations | 2 | 4 | 2 | 4 | 100
| Stakeholder meetings & approvals | 3 | 2 | 3 | 2 | 100
| Create project timeline & cost estimation | 4 | 3 | 4 | 3 | 100
System Design & Architecture | Define system architecture | 5 | 5 | 5 | 5 | 100
| Design data flow & API communication | 5 | 3 | 5 | 3 | 90
| Database schema & storage selection | 5 | 3 | 5 | 3 | 100
| Develop security & access control strategy | 5 | 2 | 5 | 2 | 100
| Finalize frontend UI/UX wireframes | 7 | 3 | 7 | 3 | 100
Backend Development | Setup AWS SDK & configure Security Hub API | 10 | 5 | 10 | 5 | 100
| Develop backend APIs using Node.js & Express | 11 | 3 | 11 | 3 | 90
| Implement authentication & authorization | 11 | 3 | 11 | 3 | 80
| Integrate Security Hub, SNS, Logging | 13 | 4 | 13 | 4 | 75
| Implement business logic & analytics | 9 | 3 | 9 | 3 | 70
Frontend Development | Setup React.js with UI components | 15 | 3 | 15 | 3 | 90
| Implement dashboard for insights visualization | 12 | 3 | 12 | 3 | 80
| Connect frontend with backend APIs | 17 | 2 | 17 | 2 | 70
| Implement RBAC | 18 | 3 | 18 | 3 | 60
| Perform UI/UX testing and optimizations | 14 | 2 | 14 | 2 | 60
Cloud Deployment & Infrastructure | Deploy backend on AWS Lambda / EC2 / Fargate | 19 | 2 | 19 | 2 | 50
| Deploy frontend on S3 & CloudFront | 20 | 3 | 20 | 3 | 40
| Setup CI/CD pipeline | 22 | 3 | 22 | 3 | 30
| Configure monitoring | 23 | 3 | 23 | 3 | 25
| Perform security audit & compliance checks | 24 | 2 | 24 | 2 | 20
Testing & Quality Assurance | Unit testing | 25 | 2 | 25 | 2 | 10
| API testing | 25 | 2 | 25 | 2 | 10
| Load testing | 24 | 2 | 24 | 2 | 5
| Security testing | 28 | 2 | 28 | 2 | 0
| User acceptance testing | 24 | 2 | 24 | 2 | 0
| Prepare system architecture document | 26 | 2 | 26 | 2 | 0
Documentation & Final Review | Write API documentation | 30 | 2 | 30 | 2 | 0
| Prepare cost analysis report | 32 | 2 | 31 | 2 | 0
| Create user & developer guides | 33 | 2 | 33 | 2 | 0
| Final project presentation & review | 25 | 2 | 25 | 2 | 0

## Sheet1
Task ID | Task Name | Estimated Duration (Days) | Depends On Task ID(s)
1 | Define project objectives & scope | 2 | -
2 | Identify AWS security services & integrations | 3 | 1
3 | Stakeholder meetings & approvals | 4 | 2
4 | Create project timeline & cost estimation | 2 | 3
5 | Define system architecture | 3 | 4
6 | Design data flow & API communication | 5 | 5
7 | Database schema & storage selection | 3 | 5
8 | Develop security & access control strategy | 3 | 5
9 | Finalize frontend UI/UX wireframes | 2 | 5
10 | Setup AWS SDK & configure Security Hub API | 3 | 7
11 | Develop backend APIs using Node.js & Express | 5 | 10
12 | Implement authentication & authorization | 3 | 11
13 | Integrate Security Hub, SNS, Logging | 3 | 11
14 | Implement business logic & analytics | 4 | 13
15 | Setup React.js with UI components | 3 | 9
16 | Implement dashboard for insights visualization | 3 | 15
17 | Connect frontend with backend APIs | 3 | 12,16
18 | Implement RBAC | 2 | 17
19 | Perform UI/UX testing and optimizations | 3 | 18
20 | Deploy backend on AWS Lambda / EC2 / Fargate | 2 | 14
21 | Deploy frontend on S3 & CloudFront | 2 | 19
22 | Setup CI/CD pipeline | 3 | 20,21
23 | Configure monitoring | 3 | 22
24 | Perform security audit & compliance checks | 3 | 23
25 | Unit testing | 2 | 24
26 | API testing | 2 | 25
27 | Load testing | 2 | 25
28 | Security testing | 2 | 24
29 | User acceptance testing | 2 | 28
30 | Prepare system architecture document | 2 | 24
31 | Write API documentation | 2 | 26
32 | Prepare cost analysis report | 2 | 30
33 | Create user & developer guides | 2 | 31,32
34 | Final project presentation & review | 2 | 33