## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
MILESTONE | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Requirement Analysis & Planning | Define project objectives & scope | 1 | 2 | 1 | 2 | 100 | bar: PERIODS 1 to PERIODS 5
| Identify AWS security services & integrations | 1 | 3 | 1 | 3 | 100
| Stakeholder meetings & approvals | 2 | 3 | 2 | 4 | 100
| Create project timeline & cost estimation | 3 | 2 | 3 | 2 | 100
System Design & Architecture | Define system architecture | 4 | 3 | 4 | 3 | 100
| Design data flow & API communication | 5 | 4 | 5 | 5 | 90
| Database schema & storage selection | 6 | 2 | 6 | 3 | 100
| Develop security & access control strategy | 7 | 2 | 7 | 3 | 100
| Finalize frontend UI/UX wireframes | 7 | 2 | 7 | 2 | 100
Backend Development | Setup AWS SDK & configure Security Hub API | 8 | 3 | 8 | 3 | 100
| Develop backend APIs using Node.js & Express | 9 | 4 | 9 | 5 | 90
| Implement authentication & authorization | 10 | 3 | 10 | 3 | 80
| Integrate Security Hub, SNS, Logging | 11 | 3 | 11 | 3 | 75
| Implement business logic & analytics | 12 | 4 | 12 | 4 | 70
Frontend Development | Setup React.js with UI components | 8 | 3 | 8 | 3 | 90
| Implement dashboard for insights visualization | 9 | 3 | 9 | 3 | 80
| Connect frontend with backend APIs | 10 | 3 | 10 | 3 | 70
| Implement RBAC | 11 | 2 | 11 | 2 | 60
| Perform UI/UX testing and optimizations | 12 | 3 | 12 | 3 | 60
Cloud Deployment & Infrastructure | Deploy backend on AWS Lambda / EC2 / Fargate | 13 | 2 | 13 | 2 | 50
| Deploy frontend on S3 & CloudFront | 13 | 2 | 13 | 2 | 40
| Setup CI/CD pipeline | 14 | 3 | 14 | 3 | 30
| Configure monitoring | 15 | 3 | 15 | 3 | 25
| Perform security audit & compliance checks | 16 | 3 | 16 | 3 | 20
Testing & Quality Assurance | Unit testing | 17 | 2 | 17 | 2 | 10
| API testing | 18 | 2 | 18 | 2 | 10
| Load testing | 19 | 2 | 19 | 2 | 5
| Security testing | 20 | 2 | 20 | 2 | 0
| User acceptance testing | 21 | 2 | 21 | 2 | 0
| Prepare system architecture document | 22 | 2 | 22 | 2 | 0
Documentation & Final Review | Write API documentation | 22 | 2 | 22 | 2 | 0
| Prepare cost analysis report | 23 | 2 | 23 | 2 | 0
| Create user & developer guides | 24 | 2 | 24 | 2 | 0
| Final project presentation & review | 25 | 2 | 25 | 2 | 0