## Table 1
Risk Management Matrix
NAME | Simplified and Centralized AWS Security Hub Insights
|  | PRE - MITIGATION |  |  |  |  | POST-MITIGATION
REF ID | RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | MITIGATIONS / WARNINGS / REMEDIES | DEPARTMENT/LOCATIO N | POST-MITIGATION RISK SEVERITY | POST-MITIGATION RISK LIKELIHOOD | POST-MITIGATION RISK LEVEL | ACCEPTABLE TO PROCEED?
|  | – ACCEPTABLE – TOLERABLE – UNDESIRABLE – INTOLERABLE | IMPROBABLE – POSSIBLE – PROBABLE | – LOW – MEDIUM – HIGH – EXTREME |  |  | – ACCEPTABLE – TOLERABLE – UNDESIRABLE – INTOLERABLE | – IMPROBABLE – POSSIBLE – PROBABLE | – LOW – MEDIUM – HIGH – EXTREME | YES / NO
1 | Limited out-of-the-box reporting options | Tolerable | Possible | Medium | Implement AWS Lambda and CloudWatch for custom reporting. Utilize AWS SDKs for automation. | Security Operations, IT | Acceptable | Improbable | Low | YES
2 | Inability to customize dashboards to fit specific needs | Tolerable | Possible | Medium | Use AWS CloudWatch Dashboards to create custom views. Train teams on dashboard creation. | Security Operations | Acceptable | Improbable | Low | YES
3 | Inadequate integration with third-party security tools | Undesirable | Probable | High | Integrate with third-party tools like Splunk and ServiceNow using AWS Security Hub. | Security, IT Operations | Tolerable | Possible | Medium | YES
4 | Limited visibility into findings and trends | Undesirable | Probable | High | Use AWS Security Hub insights to filter and prioritize findings based on severity. | Security Operations | Tolerable | Possible | Medium | YES
5 | Complexity of configuring customized alerts | Tolerable | Possible | Medium | Use AWS Lambda and AWS Systems Manager to automate alert configuration. Provide training on configuration. | IT Operations | Acceptable | Improbable | Low | YES
6 | Inefficient tracking of remediation progress | Intolerable | Probable | Extreme | Implement AWS Config to automate and track remediation tasks. Use Systems Manager for continuous tracking. | Security Response, IT | Undesirable | Probable | High | NO
7 | Delay in identifying critical vulnerabilities | Undesirable | Probable | High | Implement automated vulnerability scanning using AWS Inspector and GuardDuty. | IT Security, Incident Response | Tolerable | Possible | Medium | YES
8 | Manual processes to generate and distribute security reports | Tolerable | Possible | Medium | Automate report generation using AWS Lambda and CloudWatch to schedule and distribute reports. | Security Operations | Acceptable | Improbable | Low | YES
9 | Difficulty in associating findings with specific remediation tasks | Undesirable | Probable | High | Integrate AWS Systems Manager and Jira for task tracking and assignment. | Security Response | Tolerable | Possible | Medium | YES
10 | Inconsistent reporting between accounts and regions | Tolerable | Possible | Medium | Use AWS Config and AWS Security Hub with centralized dashboards for cross-region reporting. | Multi-region teams | Acceptable | Improbable | Low | YES
11 | Lack of automated reporting for management review | Undesirable | Probable | High | Automate reports using AWS CloudWatch and Lambda for continuous generation and distribution. | IT Security Management | Tolerable | Possible | Medium | YES
12 | Overload of irrelevant findings in dashboards | Tolerable | Possible | Medium | Implement automated filtering for alerts based on severity and criticality using AWS Security Hub. | Security Operations | Acceptable | Improbable | Low | YES
13 | Inability to integrate findings into existing incident response workflows | Undesirable | Probable | High | Use AWS Step Functions to integrate findings with incident response workflows and alert teams. | Security, Operations | Tolerable | Possible | Medium | YES
14 | Difficulty tracking and maintaining security compliance over time | Intolerable | Probable | Extreme | Leverage AWS Config for continuous compliance monitoring and automated reporting. | IT Compliance | Undesirable | Probable | High | NO
15 | Lack of ability to generate historical reports for trend analysis | Tolerable | Possible | Medium | Set up AWS S3 and Athena for storing and querying historical security data for trend analysis. | Data Analysts, Security | Acceptable | Improbable | Low | YES
16 | Lack of granularity in control over security alerts | Tolerable | Possible | Medium | Fine-tune alerts using AWS Config and CloudWatch for greater granularity and specificity. | Security Operations | Acceptable | Improbable | Low | YES
17 | Delayed detection of anomalous activity due to poor visibility | Undesirable | Probable | High | Use AWS GuardDuty for enhanced anomaly detection and integrate findings with Security Hub. | Security Monitoring | Tolerable | Possible | Medium | YES
18 | Failure to align security findings with regulatory requirements | Intolerable | Probable | Extreme | Use AWS Audit Manager for continuous compliance tracking and automated audit reporting. | Compliance, Security | Undesirable | Probable | High | NO
19 | Inability to prioritize findings based on risk levels | Undesirable | Probable | High | Use AWS Security Hub Insights to categorize and prioritize findings based on risk severity. | Security, Incident Response | Tolerable | Possible | Medium | YES
20 | Lack of effective monitoring of AWS environment-wide security posture | Undesirable | Probable | High | Implement continuous monitoring using AWS Security Hub combined with GuardDuty and Config. | Security Monitoring | Tolerable | Possible | Medium | YES